## 3.17-3.24
Yangwei | Data Configure
Hero panel
Weapon & Booster panel
User data Local storage
JiaNan
Hero Avatar (Idle, Gournd hit, Air hit)
In game UI replacement
Langyefan | Navigation UI document

## 3.25-4.1
Yangwei | Forge System
Customizable Weapon And booster storage
Avatar weapon replacement
Item Enhancement System
Xp & Coins collection
Items Buy
LevelUp (Configs and logic)
JiaNan
Avatar animation complete (start hit, gournd hit, air hit)
Floor enemy, Fly enemy design
Langyefan | Items(Heros, Weapons, Boosters, Skills) Config
Global constants definition